## Weekly Sprint Plan
Week | Sprint | Dev A (backend-lead) | Dev B (frontend-lead) | Milestones due (end of week) | Sprint goal / demo | Risks & notes
W1 | S1 | M1 Desk entity groundwork: stable chair IDs, save-time validation, migration for existing layouts | M6 Reporting data layer (start): occupancy_daily schema + nightly aggregator; kick off HReVO dept/BU data-contract conversation | M1 | Foundation demo: every chair has a stable ID; aggregation job writes first facts | HReVO data contract is the long pole for dept/BU cuts - escalate if no response by W2
W2 | S1 | M2 Desk blocking & maintenance windows: desk_blocks table, conflict handling, layout-editor controls | M6 finish + M7 Dashboard v2 core (start): trends + peak heatmap components | M2, M6 | Sprint 1 demo: block a desk from the editor; see 30-day occupancy trend | Check opsSuite ticketing linkage before building a separate maintenance model
W3 | S2 | M3 Grace-period & policy config: per-facility/per-site grace schema + admin UI (per-location config, not global) | M7 finish: drill-down building/floor/dept, auto-refresh | M3, M7 | Admin can set grace per site; dashboard v2 usable | Grace defaults (15 vs 30) left configurable - pilot data decides in W11
W4 | S2 | M10 Check-in data model + M11 check-in/out API (start): window validation, status transitions | M8 Excel/PDF export service (server-side PDF via puppeteer/pdfkit) | M10, M8 | Sprint 2 demo: check-in via API works end-to-end in Postman; export any report | PDF rendering lib choice spiked early in the week (2h timebox)
W5 | S3 | M11 finish: check-in button on booking cards/detail, admin override | M9 Scheduled report distribution: subscriptions admin UI + cron renderer | M11, M9 | User checks in from the UI; nightly report email lands in inbox | Reuse pre-end-notify cron pattern + CRON_SECRET
W6 | S3 | M12 Auto-release sweeper: FOR UPDATE SKIP LOCKED, idempotent, LOG-ONLY mode first | M4 Floor-level availability map (start): aggregate facility layouts per floor | M12 | Sprint 3 demo: sweeper releasing in log-only mode; audit trail of would-release events | Sweeper ships log-only - enforcement decision deferred to pilot (W11)
W7 | S4 | M13 Booking audit log: append-only table wired into create/check-in/release/cancel/reschedule + admin viewer (align schema with HReVO audit format) | M4 finish: colour-coded live floor map with polling | M13, M4 | Full audit trail visible; floor map live | Confirm HReVO audit format sample before schema freeze (Mon W7)
W8 | S4 | M14 Released-bookings report + M17 reminder engine (pre-start + check-in expiry) | M15 QR check-in/out: QR generation + printable labels + scan page (payload = stable desk/floor ID) | M14, M17, M15 | Sprint 4 demo: full R1 loop - remind, no-show, release, report; QR scan checks you in | QR labels: print pilot floor's labels this week for W11 pilot
W9 | S5 | M18 Release notifications + M19 admin occupancy alerts. In parallel: START M22 Count discovery (biometric) - meetings, not code | M16 Team seating visibility / find-a-colleague on floor map (permission-gated, opt-out) | M18, M19, M16 | Colleague search live; admins get threshold alerts | M22 discovery MUST conclude by end of W10 to keep Phase 2 on schedule
W10 | S5 | M20 Central monitoring dashboard (released counters, audit feed, alert feed) + buffer/bug burn-down | M5 Mobile optimization pass: booking flow, seat picker, check-in screens | M20, M5 | Sprint 5 demo: complete Phase 1 walkthrough on a phone | Freeze Phase 1 scope Friday W10
W11 | S6 | M21 Phase 1 stabilization & UAT: regression + load test on sweeper; pilot floor goes ENFORCE mode | M21: UAT support, fix queue, pilot monitoring; compare would-release logs vs reality to tune grace | M21 | Phase 1 SHIPPED to pilot; grace default decided from data | Go/no-go for tenant-wide enforce at end of W11
W12 | S6 | M22 conclude: Count vs vendor decision + connector design + employee-ID mapping | M23 Attendance ingestion (start): attendance_records schema + sync job skeleton | M22 | Sprint 6 demo: signed-off attendance interface contract | If vendor path chosen, client must provide API access this week
W13 | S7 | M24 Reconciliation engine: nightly attendance x bookings join -> utilized/no-show/walk-in | M23 finish: dedupe, employee mapping, failure alerts | M23, M24 | First reconciliation run over pilot-floor data | Use W11 pilot data as reconciliation test fixture
W14 | S7 | M25 No-show analytics & compliance reports (dashboard + exports) | M26 Badge / multi-method check-in extension riding the Count integration | M25, M26 | Sprint 7 demo: badge swipe checks you in; no-show report by dept | M26 scope flexes based on what Count hardware exposes
W15 | S8 | M27 Phase 2 UAT & rollout: end-to-end regression, deployment, handover docs | M27: UAT support, fix queue, benchmark re-run vs vendor report | M27 | SHIP: full R1-R6 live; re-scored against 33-feature benchmark (~18+/33 expected) | Book client UAT calendar in W13, not W15
Assumptions: 2 developers (A backend-lead, B frontend-lead), 2-week sprints S1-S8, ~4 productive days/dev/week. Total capacity ~120 dev-days vs 122 planned dev-days - W10 buffer + flexible M26 scope absorb the delta. Phase 1 = W1-W11 (pilot ship), Phase 2 = W12-W15. M22 Count discovery deliberately overlaps W9-W12 to de-risk Phase 2. Sprint goals are demoable statements - if the demo sentence can't be shown on screen, the sprint isn't done.