## Phased Sequence
Seq | Phase | Priority | Area | Milestone | Milestone Name | Scope (summary) | Depends On | Effort (dev-days) | Notes / Adjustments
PHASE 1 - CORE / GENERIC
1 | Phase 1 | P0 | Foundation | M0.1 | Desk entity groundwork | Stable unique desk/chair IDs in layout_json + save-time validation; migration for existing layouts. | - | 4 | Prerequisite for admin desk blocking, maps, check-in, QR and desk-level reporting. Runs first regardless of priority.
2 | Phase 1 | P1 | Admin Controls | M5.2 | Desk blocking & maintenance windows | Desk/chair block status + date-ranged maintenance windows with reason; conflict handling for existing bookings; controls in layout editor. | M0.1 | 5
3 | Phase 1 | P1 | Admin Controls | M5.1 | Grace-period & policy config UI | Grace period, release rules and reminder offsets in facility/tenant admin screens. | M0.1 | 4 | Adjusted: the grace_period_minutes + check-in schema (originally part of M1.1) is bundled here so admin config ships first. Effort +1d.
4 | Phase 1 | P2 | User Experience | M4.1 | Floor-level availability map | Aggregate per-facility layouts into a floor map; colour-coded availability; polling refresh. | M0.1 | 6 | WebSocket/SSE live push deferred to Phase 2 if needed.
5 | Phase 1 | P2 | User Experience | M4.3 | Mobile optimization pass | Booking flow, seat picker, check-in screens optimized for phones; responsive audit. | M4.1 | 5 | Check-in screen polish lands after M1.2.
6 | Phase 1 | P3 | Analytics | M3.1 | Reporting data layer | Historical daily occupancy aggregates with building/floor/department/BU dimensions; date-range APIs. | - | 6 | Occupancy/peak metrics don't need release data - can start immediately. No-show/released facts appended in Phase 2.
7 | Phase 1 | P3 | Analytics | M3.2a | Dashboard v2 - core | Occupancy trends, peak-period heatmap, drill-down by building/floor/dept; auto-refresh. | M3.1 | 5 | Split from M3.2: no-show & released-bookings views move to Phase 2 (M3.2b).
8 | Phase 1 | P4 | Auto-Release | M1.1 | Check-in data model | checked_in_at / checked_out_at columns + status transitions (schema for grace config already done in M5.1). | M5.1 | 3 | Effort -1d (schema partly delivered in M5.1).
9 | Phase 1 | P4 | Auto-Release | M1.2 | Check-in / check-out API + UI | POST check-in/check-out with window validation; check-in button on booking cards/detail; admin override. | M1.1 | 5
10 | Phase 1 | P4 | Auto-Release | M1.3 | Auto-release sweeper | Release approved bookings past start+grace with no check-in; free seat/capacity; idempotent + race-safe. | M1.2 | 5
11 | Phase 1 | P5 | Notifications | M6.1 | Reminder engine | Pre-start booking reminder + check-in expiry reminder; per-tenant offsets. | M1.2 | 4
12 | Phase 1 | P5 | Notifications | M1.4 | Release notifications | Pre-release warning ('check in within X min') + post-release email, wired into sweeper. | M1.3 | 3
13 | Phase 1 | P0 | Cross-cutting | MX.1a | Phase 1 stabilization | Regression + load test on sweeper, pilot floor rollout, fixes. | All P1 | 4 | Split from MX.1.
PHASE 2 - ADVANCED
14 | Phase 2 | P1 | Admin Controls | M5.3 | Central monitoring dashboard | Admin console: live released/no-show counters, audit log feed, alert feed. | M1.5, M3.1 | 4
15 | Phase 2 | P1 | Admin Controls | M1.5 | Booking audit log | booking_audit_log table; events for create/check-in/release/cancel/reschedule; admin viewer + export. | M1.3 | 4 | Moved under Admin priority as it is an admin/compliance feature.
16 | Phase 2 | P2 | User Experience | M4.2 | QR check-in / check-out | QR per desk/facility, printable labels; mobile scan page -> check-in/out API. | M1.2 | 5
17 | Phase 2 | P2 | User Experience | M4.4 | Team seating visibility | 'My team today' on floor map; permission gating + privacy opt-out. | M4.1 | 4
18 | Phase 2 | P3 | Analytics | M3.2b | Dashboard v2 - no-show & released views | No-show analysis + released-bookings report added to dashboard. | M1.3, M2.3 | 3 | Full no-show accuracy requires biometric reconciliation (M2.3); released-bookings view works from M1.3 alone.
19 | Phase 2 | P3 | Analytics | M3.3 | Excel/PDF export | Generalized export service for all reports; server-side PDF rendering. | M3.2a | 4
20 | Phase 2 | P3 | Analytics | M3.4 | Scheduled report distribution | Admin-configurable subscriptions; cron renders Excel/PDF and emails. | M3.3 | 4
21 | Phase 2 | P5 | Notifications | M6.2 | Admin occupancy alerts | Threshold alerts (occupancy %, no-show rate) emailed to admins; per-tenant config. | M3.1 | 3
22 | Phase 2 | P6 | Biometric | M2.1 | Discovery + connector design | Confirm vendor & integration mode; employee-ID mapping; interface contract. | Client input | 5 | Client dependency - can start discovery in parallel during Phase 1 to de-risk.
23 | Phase 2 | P6 | Biometric | M2.2 | Attendance ingestion service | attendance_records table; scheduled sync; dedupe + employee mapping; failure alerts. | M2.1 | 6
24 | Phase 2 | P6 | Biometric | M2.3 | Reconciliation engine | Daily join of attendance vs bookings; classify utilized / no-show / walk-in. | M2.2, M1.3 | 6
25 | Phase 2 | P6 | Biometric | M2.4 | Compliance & utilization reports | Utilized vs no-show vs walk-in by dept/site/date-range; Excel export. | M2.3 | 4
26 | Phase 2 | P0 | Cross-cutting | MX.1b | Phase 2 UAT & rollout | End-to-end regression, client UAT, deployment, handover. | All P2 | 6 | Split from MX.1.
[6 empty] | Phase 1 total |  | 59
[6 empty] | Phase 2 total |  | 58
[6 empty] | Grand total |  | 117
Priority order (per Rishabh, 18-Aug): P1 Admin Controls > P2 User Experience > P3 Analytics > P4 Auto-Release > P5 Notifications > P6 Biometric (rest). Phase 1 = generic/core features; Phase 2 = advanced. Adjustments made for hard dependencies: grace-period schema pulled into M5.1; M3.2 split into core (Ph1) and no-show/released views (Ph2); M1.5 audit log grouped under Admin in Ph2; MX.1 UAT split per phase. Draft for validation - edit Seq/Phase cells directly and effort will re-total.

## Gap Analysis
Req # | Requirement (from BRD) | Status | What We Already Have (code evidence) | Gap / What Needs To Be Built
0. Platform Foundation (context)
0.1 | Core booking platform (multi-tenant, roles, booking engine) | Achieved | Node/Express + MySQL + React. Full booking module (bookings.controller.js, 1500+ lines): create, availability check, cancel, reschedule-via-email, shared/capacity bookings with race-safe transactions, multi-step approval chains, per-chair seat selection with clash detection (DESK_TAKEN) and VIP chairs. Roles: super_admin / tenant_admin / org_admin / approver / employee with tenant/org scoping. | None - solid foundation to build on. Note: system is facility/room-centric; a 'desk' today is a chair inside facilities.layout_json, not a first-class entity. Recommend introducing a proper desk entity (or formalising chair IDs) as groundwork for check-in, biometrics and desk-level reporting.
1. Automatic Release of Unutilized Desk Bookings
1.1 | Check-in to booked desk within configurable grace period (15/30 min) | Not Achieved | No user check-in exists. The words 'checkin/checkout' in code refer only to approval-workflow stages (facility_approval_chains). Reusable pieces: in-process job runner (jobs/checkoutSweeper.js, 5-min interval) and secured cron endpoint (POST /api/cron/pre-end-notify with CRON_SECRET). | Check-in/check-out data model (checked_in_at, checked_out_at), check-in API + UI button, per-facility/tenant grace_period_minutes config, admin override.
1.2 | Auto-release booking if no check-in within grace period | Not Achieved | bookings.status enum includes 'completed' but it is never written by any code path; nothing ever releases or completes a booking. Sweeper pattern exists and can be extended. | Auto-release sweeper: find approved bookings past start_at + grace with no check-in, set status='released', free the seat/capacity so others can book, handle shared-capacity bookings correctly.
1.3 | Notifications before and after booking release | Partial | Strong email layer: nodemailer (utils/mailer.js), 12+ templates (mailTemplates.js), recipient resolution incl. dept managers, cron-driven bookingEndingSoon already sends time-based emails. | Two new templates + triggers: 'check in within X min or your desk will be released' (pre-release warning) and 'your booking was released' (post-release). Wire into sweeper.
1.4 | Complete audit logs for all released bookings | Not Achieved | No audit/activity-log table anywhere. Only created_at/updated_at on bookings and decided_at on approvals. | booking_audit_log table (booking_id, event, actor [user/system], old/new status, timestamp, metadata JSON), written on create/check-in/release/cancel/reschedule. Admin audit viewer + export.
2. Biometric Attendance Integration
2.1 | Integrate desk booking with biometric attendance system | Not Achieved | Nothing exists. Zero references to biometric/attendance in backend, frontend, docs or services. | Attendance connector (vendor API / DB view / CSV-SFTP import - to be confirmed with client which biometric system they use), attendance_records table, scheduled sync job, employee-ID mapping between HR/biometric IDs and users.
2.2 | Validate actual office attendance against desk reservations | Not Achieved | Nothing exists. | Daily reconciliation engine joining attendance punches to bookings per user/site/date.
2.3 | Identify booked-and-utilized, no-shows, walk-ins | Not Achieved | Only artefact: offline_capacity column comment mentions walk-ins as a manually held-back seat count - no detection or reporting. | Classification logic: attended + booked = utilized; booked + no punch (or released) = no-show; punch + no booking = walk-in. Persist daily results for reporting.
2.4 | Attendance compliance and utilization reports | Not Achieved | Nothing exists. | Compliance report screens + export (per dept/site/date-range), feeding into the analytics dashboard (Req 3).
3. Advanced Analytics and Reporting Dashboard
3.1 | Real-time occupancy and utilization dashboard | Partial | GET /api/dashboards/tenant-admin: total/occupied/free now + today's booked-vs-open minutes per facility; DashboardPage.tsx with KPI tiles, recharts drill-down, facility pies; Gantt timeline view (F08). Today-only, refresh on load. | Historical date-range metrics, occupancy trend over time, auto-refresh/live updates, desk-level (vs facility-level) utilization.
3.2 | Analytics by location, building, floor, department, business unit | Partial | Filters exist for tenant / organisation / site (TenantScopeContext, MastersFilterContext). Buildings, floors, departments all exist as master entities; bookings store department_id. | Aggregation + drill-down by building, floor, department, business unit (BU concept may need adding to masters). No report today uses department_id.
3.3 | Reports: occupancy trends, no-show analysis, released bookings, peak utilization | Not Achieved | None exist (README itself lists 'tenant reports - utilisation, no-shows, peak hours' as still to build). No-show/released data depends on Req 1 & 2 being built. | Reporting module with 4 report types, date-range + dimension filters. Depends on check-in/release events (Req 1) and attendance reconciliation (Req 2).
3.4 | Export functionality in Excel/PDF | Partial | xlsx library already in frontend; used once - FacilitiesListPage.tsx exports the facilities master list to Excel. | Generalized export for all reports/dashboards; PDF generation (none exists - add server-side e.g. puppeteer/pdfkit).
3.5 | Scheduled report distribution via email | Not Achieved | Only scheduled email is cron pre-end-notify (booking ending soon). Mailer infra is solid. | Report scheduler: admin-configurable subscriptions (report, frequency, recipients), cron job rendering report to Excel/PDF and emailing it.
4. Enhanced User Experience
4.1 | Interactive floor maps with real-time desk availability | Partial | Strongest area. DeskLayoutEditor.tsx (~1500 lines): admin 2D SVG editor - floor image upload, drag/rotate/resize desks/chairs/walls, scale in metres, VIP marking; CV auto-detection of chairs/tables via floor-scan-svc (FastAPI + OpenCV, proxied at POST /api/floor-scan). DeskPicker.tsx: booker view, chairs colour-coded available/occupied/selected per chosen time window (via GET /api/bookings/check). Unwired extras: three.js 3D Floor Studio shell (no persistence), Mask R-CNN service (not routed). | Maps are per-facility, not per-floor - add floor-level map aggregating all desks; live refresh (polling or WebSocket/SSE - none exists today); availability currently refreshes only on user interaction.
4.2 | Search and filter by location, floor, etc. | Achieved | GET /api/bookings with q/status/facility/date filters + scope (mine/team/tenant); BookingsTable tabs + search; cascading tenant->org->site filters; public portal browsing. | Minor: add floor/building as explicit booking-search filters if required.
4.3 | Mobile-responsive booking experience | Partial | AppLayout.tsx: hamburger + off-canvas drawer at md: breakpoint, responsive padding; Tailwind throughout. | Seat-map (SVG picker) and DataGrid-heavy pages not optimized for phones; needs a mobile pass on booking flow + check-in screens.
4.4 | QR code-based check-in and check-out | Not Achieved | No QR library, route, or dependency anywhere. | QR generation per desk/facility (printable labels), scan -> auth -> check-in/out endpoint (builds on Req 1.1), camera-based scan page for mobile.
4.5 | Team members' seating visibility (permission-gated) | Partial | GET /api/bookings?scope=team returns dept bookings for department managers (departments.manager_user_id); RoleGate permission components exist. | 'Where is my team sitting today' view on the floor map for regular employees, with privacy/permission controls (opt-out, role gating).
5. Administrative Controls
5.1 | Configurable booking rules and grace periods | Partial | Booking rules well covered: per-facility min_advance_minutes, max_advance_days, max bookings per user per day/week/month (032, enforced in checkAdvanceRules incl. on reschedule); per-slot capacity overrides; operating hours + slot_minutes; requires_approval; T&Cs. | Grace-period configuration does not exist (no column/field) - add per-facility/tenant setting + admin UI (part of Req 1).
5.2 | Desk blocking and maintenance management | Not Achieved | Closest equivalents: facility status 0/1 (whole facility on/off), offline_capacity (hold back N seats), VIP flag (hide chair from bookers). No maintenance state, no date-ranged blocking. | Desk/chair-level block status + date-ranged maintenance windows (blackout periods), reason tracking, auto-conflict handling for existing bookings, admin UI on the layout editor.
5.3 | Reservation limits and policy-based controls | Achieved | Fully exists: per-user daily/weekly/monthly booking caps, advance-window rules, approval workflows per facility, admin bypass. Enforced server-side. | None significant. Optionally extend policies to department level.
5.4 | Centralized administration dashboard | Partial | Admin dashboard (occupancy today + Gantt) plus full masters CRUD (tenants/orgs/sites/buildings/floors/facilities/departments/users/pantries), approval chain editor, slot capacity editor. | Consolidated monitoring view: released bookings, no-shows, alerts, audit log - grows out of Req 1-3 deliverables.
6. Notifications and Alerts
6.1 | Booking confirmations and reminders | Partial | Confirmations are rich: bookingSubmitted, approvalRequested (with one-click action tokens), bookingConfirmed (with reschedule/cancel deep links, guest fan-out), decision + FYI notifications, bookingEndingSoon cron. | No pre-start reminder ('your booking starts in 1 hour') - add reminder scheduler + template.
6.2 | Check-in reminders before booking expiry | Not Achieved | Mailer + cron infra reusable. | Depends on Req 1: reminder at booking start / T-minus-X of grace expiry.
6.3 | Auto-release notifications | Not Achieved | Mailer infra reusable. | Same as 1.3 - pre-warning + post-release emails.
6.4 | Occupancy/utilization alerts for administrators | Not Achieved | Nothing exists. | Threshold-based admin alerts (e.g. floor >90% booked, no-show rate spike), configurable per tenant.
Legend: Achieved = exists and usable today · Partial = building blocks exist, needs extension · Not Achieved = net-new build. Code evidence refers to files in the FacilityManagement repo (backend/src, frontend/src).

## Milestones
Req # | Area | Milestone | Milestone Name | Scope / Deliverables | Builds On (existing) | Depends On | Effort (dev-days) | Timeline (weeks)
0 | Foundation | M0.1 | Desk entity groundwork | Formalise desks: stable desk/chair IDs in layout_json or a desks table keyed to facility/floor; migration for existing layouts. Unblocks check-in, QR, biometrics and desk-level reporting. | facilities.layout_json chair objects; migration framework (scripts/migrate.js) | - | 4 | Wk 1
1 | Auto-Release | M1.1 | Check-in data model + grace config | Add checked_in_at/checked_out_at + status transitions to bookings; grace_period_minutes per facility with tenant default; admin config UI. | bookings table, facilities settings pattern (032 advance rules), masters admin UI | M0.1 | 4 | Wk 1-2
1 | Auto-Release | M1.2 | Check-in / check-out API + UI | POST /bookings/:id/check-in & /check-out with window validation; check-in button on booking cards + booking detail; admin manual override. | bookings.controller.js, BookingsTable.tsx | M1.1 | 5 | Wk 2-3
1 | Auto-Release | M1.3 | Auto-release sweeper | Extend job runner: release approved bookings past start+grace with no check-in (status='released'), free seat/capacity incl. shared bookings; idempotent + race-safe. | jobs/checkoutSweeper.js pattern, withTransaction/FOR SHARE locking | M1.2 | 5 | Wk 3-4
1 | Auto-Release | M1.4 | Release notifications | Pre-release warning email ('check in within X min') and post-release email; wired into sweeper. | mailer.js + mailTemplates.js + cron pre-end-notify pattern | M1.3 | 3 | Wk 4
1 | Auto-Release | M1.5 | Booking audit log | booking_audit_log table; events for create/check-in/release/cancel/reschedule (actor: user/system); admin viewer with filters + Excel export. | migration framework; DataGrid admin pages | M1.3 | 4 | Wk 4-5
2 | Biometric Integration | M2.1 | Discovery + connector design | Confirm biometric vendor & integration mode (API / DB view / CSV-SFTP); employee-ID mapping strategy; finalize interface contract with client IT. | - | Client input | 5 | Wk 3-4
2 | Biometric Integration | M2.2 | Attendance ingestion service | attendance_records table; scheduled sync job (pull or file import); dedupe + employee mapping to users; error/monitoring hooks. | cron controller (CRON_SECRET), mailer for failure alerts | M2.1 | 6 | Wk 5-6
2 | Biometric Integration | M2.3 | Reconciliation engine | Daily job joining attendance to bookings per user/site/date; classify utilized / no-show / walk-in; persist daily results. | bookings + released status (M1.3) | M2.2, M1.3 | 6 | Wk 6-7
2 | Biometric Integration | M2.4 | Compliance & utilization reports | Report screens: utilized vs no-show vs walk-in by dept/site/date-range; Excel export. | dashboards module, xlsx export pattern | M2.3 | 4 | Wk 7-8
3 | Analytics & Reporting | M3.1 | Reporting data layer | Historical aggregation (daily occupancy facts) with building/floor/department/BU dimensions; date-range APIs (today-only limitation removed). | dashboards.controller.js, buildings/floors/departments masters, department_id on bookings | M1.3 (release data) | 6 | Wk 8-9
3 | Analytics & Reporting | M3.2 | Dashboard v2 | Occupancy trends, peak-period heatmap, no-show analysis, released-bookings report; drill-down by building/floor/dept/BU; auto-refresh. | DashboardPage.tsx + recharts + Gantt | M3.1, M2.3 | 8 | Wk 9-11
3 | Analytics & Reporting | M3.3 | Excel/PDF export | Generalized export service for all reports; server-side PDF rendering (puppeteer/pdfkit). | xlsx already used in FacilitiesListPage.tsx | M3.2 | 4 | Wk 11
3 | Analytics & Reporting | M3.4 | Scheduled report distribution | Admin-configurable subscriptions (report, frequency, recipients); cron renders Excel/PDF and emails. | mailer.js, cron pattern | M3.3 | 4 | Wk 11-12
4 | User Experience | M4.1 | Floor-level live availability map | Aggregate per-facility layouts into a floor map view; colour-coded live availability; polling first (WebSocket/SSE optional phase 2). | DeskPicker.tsx, DeskLayoutEditor.tsx, GET /api/bookings/check | M0.1 | 6 | Wk 5-6
4 | User Experience | M4.2 | QR check-in / check-out | QR code per desk/facility (printable labels from admin); mobile scan page -> auth -> check-in/out API. | check-in API (M1.2) | M1.2 | 5 | Wk 4-5
4 | User Experience | M4.3 | Mobile optimization pass | Booking flow, seat picker and check-in screens optimized for phones; responsive audit of DataGrid pages. | AppLayout responsive shell, Tailwind | M4.2 | 5 | Wk 6-7
4 | User Experience | M4.4 | Team seating visibility | 'My team today' view on floor map; permission gating (role + opt-out privacy setting). | scope=team API, RoleGate.tsx, floor map (M4.1) | M4.1 | 4 | Wk 7-8
5 | Admin Controls | M5.1 | Grace-period & policy config UI | Surface grace period, release rules and reminder offsets in facility/tenant admin screens. | Facility settings UI (advance rules editor) | M1.1 | 3 | Wk 2-3
5 | Admin Controls | M5.2 | Desk blocking & maintenance windows | Desk/chair block status + date-ranged maintenance windows with reason; conflict handling for existing bookings; controls in layout editor. | DeskLayoutEditor (VIP flag pattern), facility status/offline_capacity | M0.1 | 5 | Wk 5-6
5 | Admin Controls | M5.3 | Central monitoring dashboard | Admin console tab: live released/no-show counters, audit log, alert feed. | Admin dashboard, M1.5 audit log | M1.5, M3.1 | 4 | Wk 12
6 | Notifications | M6.1 | Reminder engine | Pre-start booking reminder + check-in expiry reminder; per-tenant offsets. | mailer.js, cron pre-end-notify | M1.2 | 4 | Wk 3-4
6 | Notifications | M6.2 | Admin occupancy alerts | Threshold alerts (occupancy %, no-show rate) emailed to admins; configurable per tenant. | mailer.js, reporting layer (M3.1) | M3.1 | 3 | Wk 12
X | Cross-cutting | MX.1 | UAT, hardening & rollout | End-to-end regression, load test on sweeper/reporting queries, data migration checks, pilot floor rollout, client UAT + fixes, deployment. | docs/DEPLOY.md | All | 10 | Wk 13-14
|  |  |  | Total estimated effort |  |  | 117
Notes: Effort = focused dev-days per milestone (1 developer), excluding PM/QA overhead. Timeline assumes ~2 developers working parallel streams (Stream A: Req 1/5/6 + QR; Stream B: Req 2/3/4), giving ~14 weeks end-to-end incl. UAT. Req 2 timeline is contingent on client confirming the biometric vendor/interface by Wk 3. No third-party licence costs expected: all suggested libraries (QR, PDF, charts) are open source; biometric vendor API access to be provided by client.