## Milestones (Sequenced)
Milestone | Phase | Area | Milestone Name | Scope / Deliverables | Depends On | Effort (dev-days) | Change vs previous plan (from benchmark report)
PHASE 1 - ALL CORE FUNCTIONALITY
M1 | Phase 1 | Foundation | Desk entity groundwork | Stable unique desk/chair IDs in layout_json + save-time validation; migration for existing layouts. | - | 4 | Unchanged. Report reinforces: the stable desk ID becomes the QR payload / wayfinding key (M15).
M2 | Phase 1 | Admin Controls | Desk blocking & maintenance windows | Desk/chair block status + date-ranged maintenance windows with reason; conflict handling; controls in layout editor. | M1 | 5 | Scope note added: check linking blocked-desk status to opsSuite maintenance ticketing instead of duplicating a maintenance-state model.
M3 | Phase 1 | Admin Controls | Grace-period & policy config (schema + UI) | grace_period_minutes + check-in schema; release rules and reminder offsets in admin screens. | M1 | 4 | Scope CHANGED: grace period must be per-location / per-group config, not a global constant (multi-site clients, e.g. Sodexo 1,100+ sites).
M4 | Phase 1 | User Experience | Floor-level availability map | Aggregate per-facility layouts into a floor map; colour-coded availability; polling refresh. | M1 | 6 | Unchanged.
M5 | Phase 1 | User Experience | Mobile optimization pass | Booking flow, seat picker and check-in screens optimized for phones; responsive audit. | M4 | 5 | Note: responsive web may literally satisfy Req 4 ('mobile-responsive'); native app deferred to Phase 3 backlog.
M6 | Phase 1 | Analytics | Reporting data layer | Historical daily occupancy aggregates with building/floor/department/BU dimensions; date-range APIs. | - | 6 | Scope note added: dept/BU cuts need an HRMS field join (HReVO) - scope that data contract early, before build.
M7 | Phase 1 | Analytics | Dashboard v2 - core | Occupancy trends, peak-period heatmap, drill-down by building/floor/dept; auto-refresh. | M6 | 5 | Unchanged.
M8 | Phase 1 | Analytics | Excel/PDF export | Generalized export service for all reports; server-side PDF rendering. | M7 | 4 | Unchanged.
M9 | Phase 1 | Analytics | Scheduled report distribution | Admin-configurable subscriptions; cron renders Excel/PDF and emails. | M8 | 4 | Report upgrade: only Eptura delivers this cleanly - shipping it makes it a genuine differentiator, not just parity.
M10 | Phase 1 | Auto-Release | Check-in data model | checked_in_at / checked_out_at columns + booking status transitions. | M3 | 3 | Unchanged.
M11 | Phase 1 | Auto-Release | Check-in / check-out API + UI | POST check-in/check-out with window validation; check-in button on booking cards/detail; admin override. | M10 | 5 | Unchanged.
M12 | Phase 1 | Auto-Release | Auto-release sweeper | Release approved bookings past start+grace with no check-in; free seat/capacity; idempotent + race-safe. | M11 | 5 | Scope note added: ship with a 'log-only' observe-first mode before enforcing (Skedda rollout pattern).
M13 | Phase 1 | Auto-Release | Booking audit log | booking_audit_log table; events for create/check-in/release/cancel/reschedule; admin viewer + export. | M12 | 4 | Scope CHANGED: align audit schema with HReVO's compliance/audit format so a future combined compliance report needs no second data model.
M14 | Phase 1 | Auto-Release | Released-bookings report | Released-bookings view on dashboard (from sweeper data). | M12, M7 | 2 | Unchanged.
M15 | Phase 1 | User Experience | QR check-in / check-out | QR per desk/facility, printable labels; mobile scan page -> check-in/out API. QR payload = stable desk/floor ID (doubles as wayfinding key). | M11 | 5 | REINSTATED - was dropped in the last resequencing. Report maps QR to Req 1 + Req 4 as a Ph1 item.
M16 | Phase 1 | User Experience | Team seating visibility / find-a-colleague | 'Where is my team today' on floor map; colleague search; permission gating + privacy opt-out. | M4 | 4 | REINSTATED + widened to find-a-colleague. Report: explicitly named in Req 4 but was on no roadmap phase.
M17 | Phase 1 | Notifications | Reminder engine | Pre-start booking reminder + check-in expiry reminder; per-tenant offsets. | M11 | 4 | Unchanged.
M18 | Phase 1 | Notifications | Release notifications | Pre-release warning + post-release email, wired into sweeper; reuse action-link mailer. | M12 | 3 | Unchanged.
M19 | Phase 1 | Notifications | Admin occupancy alerts | Threshold alerts (occupancy %, later no-show rate) emailed to admins; per-tenant config. | M6 | 3 | Unchanged.
M20 | Phase 1 | Admin Controls | Central monitoring dashboard | Admin console: live released counters, audit log feed, alert feed. | M13, M6 | 4 | Unchanged (sequenced late - needs audit log + reporting layer).
M21 | Phase 1 | Cross-cutting | Phase 1 stabilization & UAT | Regression + load test on sweeper, pilot floor rollout, client UAT, fixes. | M1-M20 | 6 | Unchanged.
PHASE 2 - BIOMETRIC / ATTENDANCE
M22 | Phase 2 | Biometric | Discovery: Count-first evaluation + connector design | FIRST evaluate reusing Mobilise's own Count IoT attendance product as the device/attendance-data layer; only if unsuitable, confirm external vendor & integration mode; employee-ID mapping; interface contract. | Client input | 5 | Scope CHANGED: report flags Count reuse - could turn Ph2 into an internal integration instead of a new vendor integration. Also: no external vendor delivers named biometric integration cleanly - this is a market gap we can win.
M23 | Phase 2 | Biometric | Attendance ingestion service | attendance_records table; scheduled sync (Count API / vendor API / CSV); dedupe + employee mapping; failure alerts. | M22 | 6 | Unchanged in substance; source may be Count.
M24 | Phase 2 | Biometric | Reconciliation engine | Daily join of attendance vs bookings; classify utilized / no-show / walk-in. | M23, M12 | 6 | Unchanged.
M25 | Phase 2 | Biometric | No-show analytics & compliance reports | No-show analysis on dashboard + utilized/no-show/walk-in reports by dept/site/date-range; Excel/PDF export. | M24 | 5 | Unchanged.
M26 | Phase 2 | Biometric | Badge / multi-method check-in extension | Piggyback badge (and optionally geo/Wi-Fi) check-in on the Count/biometric integration so check-in methods extend beyond QR toward the multi-method benchmark. | M22, M11 | 4 | NEW milestone - report: benchmark expects multi-method check-in; roadmap previously scoped QR only.
M27 | Phase 2 | Cross-cutting | Phase 2 UAT & rollout | End-to-end regression, client UAT, deployment, handover. | M22-M26 | 5 | Unchanged.
|  |  |  | Phase 1 total (dev-days) |  | 91
|  |  |  | Phase 2 total (dev-days) |  | 31
|  |  |  | Grand total |  | 122
Updated after the Desk Booking Vendor Comparison Report (20-Aug-2026). Changes: M15 QR and M16 team visibility reinstated into Phase 1; M22 discovery now Count-first; M26 badge/multi-method check-in added to Phase 2; scope notes tightened on M2 (opsSuite), M3 (per-site grace), M6 (HReVO data contract), M13 (HReVO audit schema), M12 (log-only rollout). Correction to the report: meeting/conference-room booking is LIVE in SoCampus FM (it is the platform's core), not 'N/not in scope' - our benchmark score is understated. Phase 3 backlog (next sheet) holds the benchmark items not on any committed phase.

## Phase 3 Backlog (Uncommitted)
# | Candidate | What it is | Benchmark coverage (of 5 vendors) | Indicative effort | Considerations from report
1 | SSO / SAML | SAML/OIDC single sign-on (Entra, Okta, Google) | 3/5 (universal among top-3) | 8-10 d | Report: if HReVO already owns identity for Mobilise's client base, SoCampus FM may inherit SSO from there rather than building standalone - investigate first.
2 | MS365 / Outlook two-way sync | Bookings appear on Outlook/Google calendars; two-way updates | 3/5 | 8-12 d | Table stakes among top-3 vendors; pairs naturally with SSO work.
3 | MS Teams / Slack integration | Book + get reminders inside Teams/Slack | 3/5 | 10-15 d | Top-3 all have it; Teams likely higher value than Slack for target clients.
4 | Native mobile app / PWA | iOS/Android app (or installable PWA) for booking + QR scan | 4/5 | 15-25 d | Req 4 asks only for 'mobile-responsive' - literal requirement may already be met after M5; PWA is the cheap middle path.
5 | Multi-location / org hub | Cross-site portfolio view and administration | 5/5 (universal) | 6-8 d | Not in the six requirements, but flagged as a scaling requirement for multi-site clients (Sodexo 1,100+ sites). Our multi-tenant model is a head start.
6 | Access-control integration | Ingest badge/turnstile events (Honeywell/Dorlet-style) | 4/5 | 8-10 d | Prerequisite for a stronger Req 2 if Count is not used; M26 badge check-in partially covers this.
7 | Team neighborhoods / zones | Reserve floor zones per team/department | 5/5 (universal) | 5-6 d | Not explicitly asked; supports search/filter indirectly. Our team-seating zones could extend the layout editor.
8 | Team / group booking | Book multiple adjacent desks for a squad in one action | 5/5 (universal) | 5-7 d | Universal among vendors; natural extension of our multi-chair selection.
9 | Parking booking | Parking slot booking module | 5/5 (universal) | 10-15 d | Universal among vendors but not in the brief; our facility-type model (add 'parking' type) lowers the cost.
10 | Visitor management | Visitor pre-registration, host alerts, badge printing | 4.5/5 | 15-20 d | Not in the brief; consider only if productizing SoCampus FM beyond desk booking.
Phase 3 items are NOT committed - they are the 'not in scope / not confirmed' benchmark features from the vendor report, needed only for full category parity. Indicative efforts are rough sizing for discussion, not estimates. Recommend revisiting after Phase 1 ships and the comparison is re-run.