## Sprint Backlog
Week | Task ID | Milestone | Owner | Development task (what to actually build) | Done when (acceptance) | Est (d) | Depends on
W1 · Sprint 1 — Milestones due: M1 (desk groundwork) · M6 started ¦ Demo: every chair has a stable ID; first occupancy facts written
W1 | T1.1 | M1 | Dev A | Migration 046_stable_desk_ids.sql + backfill script scripts/fix_desk_ids.js: rewrite every facilities.layout_json chair to a stable unique id (FAC<facilityId>-D<seq>); add save-time validation in facilities.controller (reject duplicate/renamed ids with 400 DESK_ID_CONFLICT). | Backfill run on staging DB; saving a layout with duplicate chair ids returns 400; existing bookings.desk_id values still resolve. | 1.5 | -
W1 | T1.2 | M1 | Dev A | DeskLayoutEditor.tsx: auto-generate the stable id on add-chair, render id read-only in the chair inspector, block manual id edits; keep VIP flag behaviour untouched. | New chairs get sequential ids; editor cannot produce a duplicate; existing layouts open unchanged. | 1.5 | T1.1
W1 | T1.3 | M1 | Dev A | bookings.controller.js create/reschedule: validate requested desk_id(s) exist in the facility's layout_json (today only clash is checked). Return 400 DESK_UNKNOWN. | Booking a deleted/unknown chair id fails cleanly; DESK_TAKEN path unchanged (covered by existing FOR SHARE txn). | 1 | T1.1
W1 | T1.4 | M6 | Dev B | Migration 047_occupancy_daily.sql (day, tenant_id, site/building/floor/facility/department dims, booked/open minutes, bookings_count, released_count, checked_in_count; PK per HLD 4.1) + jobs/occupancyAggregator.js (aggregate YESTERDAY incrementally, modelled on jobs/checkoutSweeper.js loop) + POST /api/cron/aggregate-occupancy guarded by CRON_SECRET (copy cron.controller pre-end-notify pattern). | Nightly run writes one row per facility per day; re-running the same day is idempotent (REPLACE/UPSERT). | 2 | -
W1 | T1.5 | M6 | Dev B | Backfill script scripts/backfill_occupancy.js for last 90 days from bookings; document the HReVO dept/BU field contract (department_id already on bookings — confirm BU source field with HReVO team THIS WEEK, it gates T3.4 drill-downs). | 90-day history queryable; HReVO contract note committed to /docs. | 2 | T1.4
W2 · Sprint 1 — Milestones due: M2 (desk blocking) · M6 (reporting data layer) ¦ Demo: block a desk from the editor; 30-day trend renders
W2 | T2.1 | M2 | Dev A | Migration 048_desk_blocks.sql exactly per HLD 4.1 (tenant_id, facility_id, desk_id, reason, starts_at, ends_at, created_by + idx_blocks_lookup). | Migration applies + rolls forward cleanly on staging. | 0.5 | T1.1
W2 | T2.2 | M2 | Dev A | New module backend/src/modules/deskBlocks (controller/routes, follow floorScan module shape): POST /api/desk-blocks, DELETE /:id, GET ?facility_id= ; on create, reuse GET /facilities/:id/chair-bookings logic to warn about conflicting future bookings (response lists them). Gate with requirePerm('admin.block_desks') from modules/permissions. | Blocking a desk with a future booking returns the conflict list; permission matrix cell actually gates the route. | 1.5 | T2.1
W2 | T2.3 | M2 | Dev A | Frontend: block/unblock UI in DeskLayoutEditor.tsx right panel (reason select, note, until date); DeskPicker.tsx renders blocked chairs with hatch pattern + disabled (add 'blocked' state beside occupied/VIP). | Admin blocks D-014 with reason; booker sees hatched non-clickable chair immediately. | 2 | T2.2
W2 | T2.4 | M2 | Dev A | bookings.controller create: reject desk_ids intersecting an active desk_block window with 409 DESK_BLOCKED (inside the existing FOR SHARE transaction). | Race test: block + concurrent booking cannot both succeed. | 1 | T2.2
W2 | T2.5 | M6 | Dev B | GET /api/reports/occupancy?from&to&group_by=site¦building¦floor¦department in dashboards module, reading occupancy_daily (never raw bookings); tenant-scoped via scopeWhere. | Date-range query for 90 days returns <200ms on staging data; cuts sum correctly vs spot-checked raw data. | 1.5 | T1.4
W2 | T2.6 | M6 | Dev B | Analytics page (existing /dashboard): add occupancy trend line (recharts, token colors already themed) wired to the new endpoint with date-range picker. | Trend chart renders 30-day history with site filter. | 1.5 | T2.5
W3 · Sprint 2 — Milestones due: M3 (grace config) · M7 (dashboard v2 core) ¦ Demo: admin sets per-site grace; peak heatmap live
W3 | T3.1 | M3 | Dev A | Migration 049_grace_config.sql: facilities.grace_period_minutes INT NULL + checkin_open_before_min INT NULL (NULL = feature off, same convention as 032 advance rules) + tenant_settings table (tenant_id PK, default_grace_minutes, sweeper_mode ENUM('log_only','enforce') DEFAULT 'log_only', reminder_lead_min, occupancy_alert_pct, noshow_alert_pct). | Schema matches HLD 4.1/4.2; migrate.js clean. | 1 | -
W3 | T3.2 | M3 | Dev A | FacilityFormPage.tsx: new 'Check-in & auto-release' card beside the advance-rules fields — enable toggle, grace select (10/15/20/30/45/60), check-in-opens select (15/30/60). Tenant default editor on TenantFormPage. Gate save with requirePerm('admin.edit_rules'). | Per-facility grace saves + reloads; clearing falls back to tenant default (show resolved value as helper text). | 1.5 | T3.1
W3 | T3.3 | M3 | Dev A | utils/graceConfig.js: resolveGrace(facility, tenantSettings) -> {enabled, graceMin, opensMin} with unit tests (facility set / tenant default / both null). | Tests green; helper used by T4.2 and T6.1 (no duplicated resolution logic). | 1 | T3.1
W3 | T3.4 | M7 | Dev B | Dashboard v2 core on /dashboard: peak heatmap (hour x weekday matrix from occupancy_daily), drill-down selects building->floor->department (dept needs T1.5 contract), 60s auto-refresh (setInterval + RefreshContext). | Heatmap matches spot-checked data; drill-down filters all charts together. | 3 | T2.5
W3 | T3.5 | M7 | Dev B | LiveOverviewPage.tsx: replace the floors-table client-side rollup with the new /api/reports/occupancy group_by=floor endpoint (faster + consistent with analytics). | Floors table numbers equal analytics page numbers for the same scope. | 1 | T2.5
RBAC DELEGATION TRACK — interleaved W3-W7 (+6.5d, absorbed by W10 buffer + T10.2 overlap) ¦ Goal: each role only sees & grants what its super role enabled
RBAC DELEGATION TRACK — interleaved W3-W7 (+6.5d, absorbed by W10 buffer + T10.2 overlap) ¦ Goal: each role only sees & grants what its super role enabled | RB.1 | RBAC | - | DELIVERED (design session): delegation ceiling (tenant admin can never grant above the global value — save rejected + UI caps cell cycling with 'cap: team' hint) and sub-role rule (editors configure only roles below their own; tenant_admin column locked for tenant admins). permissions.controller.js EDITABLE_BY + ORDER checks; matrix API returns ceilings + editable_roles. | Already in repo — verify during code review, add unit tests for both rejection paths. | 0.5 | -
RBAC DELEGATION TRACK — interleaved W3-W7 (+6.5d, absorbed by W10 buffer + T10.2 overlap) ¦ Goal: each role only sees & grants what its super role enabled | RB.2 | RBAC | Dev B | W3: effective-permissions gating in the SPA — AuthContext fetches GET /permissions/effective at login/refresh; useCan('key') hook + <Can> wrapper; sidebar NavItems switch from hard-coded role arrays to permission keys (masters.manage, analytics.view, audit.view, roles.manage...). Unchecking a matrix cell hides the module from that role's nav on next load. | Demo: disable analytics.view for org_admin in the matrix -> org admin's nav loses Analytics without a deploy. | 1.5 | RB.1
RBAC DELEGATION TRACK — interleaved W3-W7 (+6.5d, absorbed by W10 buffer + T10.2 overlap) ¦ Goal: each role only sees & grants what its super role enabled | RB.3 | RBAC | Dev A | W4-W5: org tier — migration 054: role_permissions.organisation_id BIGINT NULL + widen unique key (tenant_id, organisation_id, role, permission_key); resolution becomes org -> tenant -> global -> code default in permissions.service; matrix UI gains org scope picker for tenant admins ('Override · <org>'); EDITABLE_BY gains org_admin: ['approver','employee'] so an org admin granted roles.manage can delegate downward — capped by the tenant grant, same ceiling rule one level down. | Chain demo: super admin grants tenant 'team'; tenant admin delegates 'team' to org_admin (cannot pick 'yes'); org admin delegates to approver within THAT cap. | 2.5 | RB.1
RBAC DELEGATION TRACK — interleaved W3-W7 (+6.5d, absorbed by W10 buffer + T10.2 overlap) ¦ Goal: each role only sees & grants what its super role enabled | RB.4 | RBAC | Dev B | W5: module enablement per tenant — tenant_modules table (tenant_id, module ENUM('bookings','approvals','analytics','reports','pantry','floor_map','audit','biometric'), enabled) + 'Modules' toggle card on TenantFormPage (super admin only); permissions.service.can() returns false when the key's module is disabled for the tenant; /permissions/effective includes modules so RB.2 nav gating hides them wholesale. | Super admin switches Pantry off for tenant X -> pantry vanishes from every role's nav + API 403s, other tenants unaffected. | 2 | RB.2
RBAC DELEGATION TRACK — interleaved W3-W7 (+6.5d, absorbed by W10 buffer + T10.2 overlap) ¦ Goal: each role only sees & grants what its super role enabled | RB.5 | RBAC | Dev A | W7 (after T7.1 audit table): write every matrix/module save into booking_audit_log as type 'policy' with the change diff (who granted what to whom, old -> new, scope) — the delegation chain becomes auditable. | Audit viewer filtered to 'Policy changes' shows the full grant history. | 0.5 | T7.1, RB.3
W4 · Sprint 2 — Milestones due: M10 (check-in model) · M8 (Excel/PDF export) ¦ Demo: check-in via API end-to-end; export any report
W4 | T4.1 | M10 | Dev A | Migration 050_checkin.sql: bookings.checked_in_at/checked_out_at DATETIME NULL + extend status ENUM with 'released' (keep 'completed'). | Existing rows untouched; enum change verified against live data on staging. | 1 | T3.1
W4 | T4.2 | M10 | Dev A | bookings.controller: POST /:id/check-in + /:id/check-out. Window: start - opensMin -> start + graceMin (resolveGrace); booker or admin (requirePerm('booking.manual_release') covers on-behalf); idempotent (second check-in returns 200 with same state); DB clock (NOW()) comparisons only. Add routes to bookings.routes.js. | Postman flow: book -> check-in inside window 200, outside window 422 CHECKIN_WINDOW; second call 200 no-op. | 2 | T4.1
W4 | T4.3 | M8 | Dev B | Export service: GET /api/reports/:kind/export?format=xlsx¦pdf (kinds: occupancy, blocked; later noshow/released). xlsx via exceljs stream, pdf via pdfkit table renderer. Frontend: Export buttons (Excel/PDF) on the analytics page reusing the existing xlsx-download pattern from FacilitiesListPage.tsx for consistency. | Both formats download for occupancy with the active filters applied; PDF has header + generated-at footer. | 3 | T2.5
W4 | T4.4 | M8 | Dev B | Wire LiveOverviewPage 'Manage desks' row + floors table to a small Excel export (same service, kind=floors). | One-click floor export lands in downloads. | 0.5 | T4.3
W5 · Sprint 3 — Milestones due: M11 (check-in UI) · M9 (scheduled reports) ¦ Demo: check in from the UI; nightly report email arrives
W5 | T5.1 | M11 | Dev A | MyBookingsPage.tsx + BookingsTable.tsx: 'Check in' button when now >= start - opensMin && status approved (countdown chip shows release deadline start+grace); 'Check out' after check-in; toast confirmations echo desk + time (anti-mismatch rule from the UI research). | Booker checks in/out from My bookings on desktop + mobile widths. | 2 | T4.2
W5 | T5.2 | M11 | Dev A | Admin override: check-in-on-behalf + manual release actions on the booking row (admin scope), writing actor into the audit stub (full audit table lands W7). | Admin can check a user in; action attributed to admin, not booker. | 1 | T4.2
W5 | T5.3 | M9 | Dev B | Migration 051_report_subscriptions.sql (tenant_id, report_kind, cadence, recipients, format, last_run_at, next_run_at) + CRUD API module reportSchedules + cron POST /api/cron/send-reports: renders via T4.3 export service, emails via utils/mailer.js (new template scheduledReport). | Creating 'Daily occupancy - 18:30 - Excel' delivers a real email with attachment from the cron endpooint. | 2.5 | T4.3
W5 | T5.4 | M9 | Dev B | Reports admin UI: 'Scheduled distribution' tab (list + create form + Send now + Remove) — prototype vReports layout, on a new /admin/reports page under Masters nav (requirePerm('reports.schedule')). | Schedule created from UI; Send now triggers the cron path and stamps last_run. | 1.5 | T5.3
W6 · Sprint 3 — Milestones due: M12 (auto-release sweeper) ¦ Demo: sweeper releasing in log-only mode with full audit trail
W6 | T6.1 | M12 | Dev A | jobs/releaseSweeper.js (60s interval like checkoutSweeper): SELECT candidates WHERE status='approved' AND checked_in_at IS NULL AND grace enabled AND NOW() > start+grace LIMIT 50 FOR UPDATE SKIP LOCKED; per row re-check inside txn; mode from tenant_settings.sweeper_mode — log_only records would_release, enforce sets status='released'. Released desks must free capacity: update availability query in /bookings/check to treat released as free. | Two app instances running sweeper never double-process (SKIP LOCKED test); released desk immediately bookable by someone else. | 2.5 | T4.2, T3.3
W6 | T6.2 | M12 | Dev A | sweeper_runs heartbeat table (run_at, scanned, released, errors, mode) + failure isolation (try/catch per booking, error counter). Integration tests: double-run idempotency; race sweeper-vs-simultaneous-check-in (check-in wins if committed first). | Heartbeat row per run; both race tests green in CI. | 1.5 | T6.1
W6 | T6.3 | M4 | Dev B | GET /api/floors/:id/live-map: all facilities on the floor + layout_json + per-chair state (free/booked/checked-in/released/blocked from desk_blocks + bookings now) in one payload (<200KB budget). | Endpoint returns full floor state in one call; cached 10s server-side. | 2 | T2.2
W6 | T6.4 | M4 | Dev B | FloorMapPage.tsx at /floors/:id/map: compose existing DeskPicker SVG renderers per facility into a floor canvas; 15s polling; skeleton shimmer while loading (anti-lag rule). | Floor 'A2' renders every facility's chairs colour-coded live. | 2 | T6.3
W7 · Sprint 4 — Milestones due: M13 (audit log) · M4 (floor map) ¦ Demo: full audit trail visible; live floor map done
W7 | T7.1 | M13 | Dev A | Migration 052_booking_audit_log.sql per HLD 4.1 (append-only; event ENUM incl. would_release/released/reminder_sent; actor_type user¦admin¦system; detail JSON) — CONFIRM field naming against HReVO's audit format Monday before freezing. audit() helper + wire into create / check-in / check-out / release / cancel / reschedule / desk-block paths. | Every lifecycle action writes exactly one row; no UPDATE path exists anywhere. | 2 | T6.1
W7 | T7.2 | M13 | Dev A | Audit viewer: /admin/audit page (DataGrid — theme skin already done), type filter chips, date range, CSV export via T4.3 service; nav item under Masters gated by requirePerm('audit.view'). | Admin filters releases-only and exports CSV. | 1.5 | T7.1
W7 | T7.3 | M4 | Dev B | Floor map finish: legend (matches prototype), zone tints from layout zones, 'you are here' highlight for own booking, mobile horizontal scroll; entry links from facility cards + Live overview floors table. | Design review passes vs prototype floor map; phone renders with scroll. | 2 | T6.4
W7 | T7.4 | M4 | Dev B | Live overview: floors table Awaiting/Released/Grace columns go LIVE (from sweeper + grace config) — remove the em-dash placeholders + footnote. | Screenshot parity with the prototype overview incl. real released counts. | 1 | T6.2, T3.3
W8 · Sprint 4 — Milestones due: M14 (released report) · M15 (QR) · M17 (reminders) ¦ Demo: full R1 loop — remind, no-show, release, report; QR scan checks you in
W8 | T8.1 | M14 | Dev A | Released-bookings report: dashboards endpoint kind=released (from audit log + bookings.status) + Live overview 'Auto-released' KPI + released live-feed card go real; add to export service kinds. | KPI equals audit-log count for today; feed rows link to audit entries. | 1.5 | T7.1
W8 | T8.2 | M17 | Dev A | Reminder engine: extend the pre-end-notify cron pattern to (a) pre-start reminder T-30 (booking.preReminded flag) and (b) check-in expiry warning at deadline - reminder_lead_min (tenant_settings) with mailTemplates additions. | Both emails fire once and only once per booking (flag test). | 2 | T4.2
W8 | T8.3 | M15 | Dev B | QR generation: GET /api/facilities/:id/desk-qr.pdf — printable label grid (qrcode npm + pdfkit), payload = https://<host>/checkin?d=<stableDeskId>&f=<facilityId> (stable id from M1 — survives rebooks); 'Print QR labels' button in DeskLayoutEditor. | Printed sheet for floor A2; phone camera opens the URL. | 2 | T1.1
W8 | T8.4 | M15 | Dev B | Scan landing route /checkin (mobile-first page): authenticated -> finds caller's active booking for that desk today -> calls the SAME POST /bookings/:id/check-in (one API, three front doors); friendly errors (not your desk / no booking / outside window). Bounce through login with ?next= (already supported). | Full phone flow: scan -> login -> checked-in confirmation echoing desk + time. | 2 | T4.2, T8.3
W9 · Sprint 5 — Milestones due: M16 (team seating) · M18 (release notices) · M19 (admin alerts) ¦ Demo: colleague search live; threshold alert email lands
W9 | T9.1 | M18 | Dev A | Release notifications: pre-release warning email with one-tap 'I'm here — keep it' action-token link (reuse booking_action_tokens infra from F07!) that performs check-in; post-release notice email. Wire both into sweeper enforce path. | Clicking the email link checks in without opening the app; released user gets notice with rebook link. | 2 | T6.1, T8.2
W9 | T9.2 | M19 | Dev A | Admin occupancy/no-show alerts: threshold check inside the aggregator/sweeper (occupancy_alert_pct, noshow_alert_pct from tenant_settings), once-per-day-per-floor dedupe, email to facility admins via mailRecipients.js. Start M22 Count discovery in parallel (meetings — book HReVO/Count API walkthrough). | Forcing occupancy over threshold on staging fires exactly one email. | 2 | T1.4, T6.1
W9 | T9.3 | M16 | Dev B | Migration 053: users.visibility ENUM('everyone','team','private') DEFAULT 'everyone'; settings UI (radio card, prototype copy); extend scope=team + new GET /api/seating/search?q= (find-a-colleague respecting visibility + dept hierarchy). | Private user invisible to peers but visible to their manager + admins. | 2 | -
W9 | T9.4 | M16 | Dev B | Floor map: teammate dots (violet) + 'My team today' filter + locate-colleague deep link from search results. | Searching a colleague highlights their desk on the right floor. | 2 | T9.3, T7.3
W10 · Sprint 5 — Milestones due: M20 (monitoring) · M5 (mobile pass) ¦ Demo: complete Phase 1 walkthrough on a phone; scope freeze Friday
W10 | T10.1 | M20 | Dev A | Live overview goes fully live: sweeper heartbeat card (sweeper_runs), audit feed, alert feed replace all remaining placeholders; log-only vs enforce toggle surfaced (tenant_settings.sweeper_mode, requirePerm('admin.edit_rules')). | Zero 'ships with Phase 1' placeholder strings left on the page. | 2 | T6.2, T7.1, T9.2
W10 | T10.2 | M20 | Dev A | requirePerm adoption sweep: swap requireRole -> requirePerm on masters CRUD, desk-blocks, reports, audit routes (defaults mirror current behaviour, so zero functional change until matrix edited). Buffer + bug burn-down. | Permission matrix edits demonstrably gate at least 6 route groups. | 2 | -
W10 | T10.3 | M5 | Dev B | Mobile pass: booking flow + seat picker touch targets (44px), check-in screens, DataGrid pages responsive audit, QR scan page polish; Lighthouse mobile >= 85 on booking flow. | PM walkthrough of book->check-in->release entirely on a phone. | 3 | T5.1, T8.4
W11 · Sprint 6 — Milestone due: M21 (Phase 1 ship) ¦ Demo: pilot floor ENFORCING; grace default decided from data
W11 | T11.1 | M21 | Both | Stabilization: regression suite over booking lifecycle; sweeper load test (5k bookings); pilot floor flips tenant_settings.sweeper_mode='enforce' (rest stay log_only); compare would_release audit rows vs reality to tune 15 vs 30 min grace; fix queue; go/no-go Friday for tenant-wide enforce. | Pilot week ends with zero wrong releases; grace default chosen from data; sign-off recorded. | 8 | All W1-W10
W12-W15 · Sprints 6-8 — PHASE 2 (biometric): M22-M27 — task detail to be cut AFTER the M22 Count-vs-vendor decision
W12-W15 | T12.x | M22 | Dev A | W12: conclude Count-first evaluation -> signed interface contract (fields per the integrations mapping: emp_code, punch_time, punch_state, terminal_sn); employee-ID mapping strategy vs users table. | Contract signed off by client IT. | 4 | W9 disc.
W12-W15 | T13.x | M23 | Dev B | W12-13: attendance_records migration + sync job (poll/delta, quarantine unmatched punches) + failure alert email. | Punches land + unmatched quarantined for review. | 6 | T12.x
W12-W15 | T14.x | M24 | Dev A | W13: reconciliation nightly job -> utilized / no-show / walk-in / on-site-not-checked-in classifications (adopt the prototype's 6-status taxonomy) using W11 pilot data as fixture. | Reconciliation over pilot week matches manual audit. | 6 | T13.x
W12-W15 | T15.x | M25-M26 | Both | W14: no-show analytics + compliance reports (dashboard + exports) and badge/multi-method check-in riding the Count integration (punch inside window = check-in when tenant enables biometricAutoCheckin). | Badge swipe checks user in on pilot floor; dept compliance report exports. | 9 | T14.x
W12-W15 | T16.x | M27 | Both | W15: Phase 2 UAT, deployment, handover docs, benchmark re-run vs the 33-feature vendor list (expect ~18+/33 -> 25+/33). | Client sign-off; re-scored benchmark circulated. | 5 | T15.x
How to read this: each row is a mergeable unit of work (0.5-3 days) with the exact file/endpoint/table to touch, written against the current repo (module names, migration numbering 046+, existing patterns to copy are named). 'Done when' is the review checklist. Owners: Dev A backend-lead, Dev B frontend-lead. requirePerm(), the permissions module, the themed UI shell, Login page, DataGrid skin and Live overview page ALREADY EXIST (see next sheet) — tasks build on them, not rebuild them. Weekly ritual: Monday - confirm the week's 'Milestones due' line; Friday - demo the sentence in the week header, or the sprint isn't done.

## Already Delivered (do not redo)
Area | What exists in the repo today (built during design sessions) | Devs should
UI theme (all screens) | SoCampus Desk tokens live in globals.css + tailwind.config.js (ink/indigo/teal palette, Space Grotesk/IBM Plex fonts, 12px radius); MUI theme.ts rewritten incl. global DataGrid skin; chips/tabs/KPI classes in components.css; legacy brand-navy classes aliased to new palette. | Use token classes (bg-indigo, text-mutedx, shadow-card...) for all new UI. Never hardcode hex.
App shell | AppLayout.tsx = prototype rail: logo block, persona card, indigo-soft active nav, light topbar, status footer. Nav: 'Live overview' + 'Analytics' for admins. | Add new pages as NavItem entries; use roles now, switch to permission keys during T10.2.
Login | LoginPage.tsx rebuilt to prototype split-panel (ink brand panel + desk-grid motif); auth flow, ?next= deep-links and /forgot-password intact (backend password_resets already existed). | Style Forgot/Reset pages to match when touched (tokens make it ~1h).
Live overview page | /overview (LiveOverviewPage.tsx): 4 KPI cards, floors table, live activity, alerts + sweeper cards. Real data: occupancy/bookings/floors/activity. Placeholders (clearly labelled) for auto-release/biometric/alerts. | W7-W10 tasks (T7.4, T8.1, T10.1) flip the placeholders live — the layout is done.
Roles & permissions | FULL-STACK DONE: migration 045_role_permissions.sql, permissions module (catalog 17 keys / service with cache + can() + requirePerm() / controller / routes), matrix UI at /admin/permissions with global + per-tenant scopes, inherited/override states, guardrails. DELEGATION MODEL ALSO DONE: ceiling rule (tenant grant capped by super admin's global grant — server-rejected AND UI-capped with 'cap' hints) + sub-role rule (edit only roles below yours; editable_roles/ceilings returned by the matrix API). | Run migrate.js. Register any new feature's permission key in permissions.catalog.js. Adopt requirePerm on new routes from day one; T10.2 sweeps legacy routes. RBAC track (RB.2-RB.5) extends this with nav gating, the org tier and per-tenant module toggles.
Gantt + dashboard | GanttTimeline + DashboardPage recharts recolored to token palette; KPI tiles restyled. | Nothing — T3.4 extends DashboardPage in place.
Reference docs | HLD (HLD_SoCampus_FM.docx) has the exact DDL for occupancy_daily/desk_blocks/audit_log + sweeper algorithm + ADRs; Milestone_Plan_Post_Benchmark.xlsx = milestone source of truth; SoCampus prototype HTML = pixel reference; SoCampus_UI_Design_Benchmark.pptx = design system. | Copy DDL from the HLD for T1.4/T2.1/T7.1 instead of re-deriving it.