## Requirement Analysis
# | Requirement Area | Key Sub-Requirements | Feasibility | Recommended Technical Approach & Architecture | Est. Effort | Licensing / Third-Party Dependencies | Timeline / Milestone
1 | Automatic Release of Unutilized Desk Bookings | • Configurable check-in grace period (15/30 min) • Auto-release if no check-in • Pre- and post-release notifications • Audit log of every released booking | High | Build a check-in action (booking → checked_in_at). Add a grace-period config (tenant/facility). A scheduled job scans bookings where now > start_at + grace AND not checked-in → set status='released', clear the desk hold, write an audit row. Reuse the existing CRON_SECRET-protected endpoint pattern + mailer. Add a 'released' status + booking_release_audit table. | 2–3 wks (M) | None new. Uses existing external scheduler + SMTP mailer. | Phase 1
2 | Biometric Attendance Integration | • Integrate biometric/attendance system • Validate attendance vs reservation • Report booked&used / no-show / walk-in • Compliance & utilization reports | Medium (vendor-dependent) | Ingestion connector for the biometric feed (vendor API / webhook / scheduled file). Store raw events in attendance_events. A reconciliation job matches events ↔ bookings ↔ check-in and classifies booked&used / no-show / walk-in. Resolve the employee-key mapping (HReVO↔users) — open question in the HReVO contract. Feed results into the reporting layer (#3). | 4–6 wks (L)+ | Biometric vendor SDK/API (THIRD-PARTY, likely licensed per-device/API — ESSL/Matrix/Suprema/etc.). HReVO mapping. Business-unit dimension sourced from HReVO. | Phase 4
3 | Advanced Analytics & Reporting Dashboard | • Real-time occupancy/utilization • Analytics by location/building/floor/dept/BU • Reports: occupancy trends, no-show, released, peak • Excel/PDF export • Scheduled email distribution | High (parts depend on #1/#2) | Extend the existing occupancy_daily rollup (already carries site/building/floor/dept dims) into a Reports module: trends over time, peak periods, no-show (needs #1 check-in data), released (needs #1). Add server-side Excel (exceljs) + PDF (pdfmake/puppeteer) renderers. Add a scheduled report job that emails rendered reports to configured recipients. BU dimension comes from HReVO (#2). | 3–5 wks (L) | exceljs (MIT), pdfmake or puppeteer (MIT/Apache) for PDF, scheduler. All OSS — no licensing cost. BU dim depends on HReVO. | Phase 2
4 | Enhanced User Experience | • Interactive floor map w/ real-time availability • Search/filter by location/floor • Mobile-responsive booking • QR check-in / check-out • Team members' seating (permission-based) | High | Floor-map picker + real-time availability + filters already exist. Add QR: generate a per-desk/per-booking QR (qrcode lib); a scan page drives the #1 check-in/out action (html5-qrcode / device camera). Add team-seating overlay (who booked which desk) gated by a new permission + privacy toggle. Harden mobile layout of the SVG picker. | 3–4 wks (M–L) | qrcode + html5-qrcode / zxing (OSS, MIT/Apache). No licensing cost. | Phase 3
5 | Administrative Controls | • Configurable booking rules & grace periods • Desk blocking & maintenance • Reservation limits & policy controls • Centralized admin dashboard | High | Reservation limits, advance rules, approval chains, slot-capacity overrides, RBAC and admin dashboards already exist. Add: grace-period config (shared with #1); per-desk blocking / maintenance windows (desk status + maintenance table — today only facility-level status/offline_capacity exists); surface everything in the central admin dashboard with alerts (#6). | 2–3 wks (M) | None new. | Phase 2
6 | Notifications and Alerts | • Booking confirmations & reminders • Check-in reminders before expiry • Auto-release notifications • Occupancy/utilization alerts for admins | High | Mailer + cron already send confirmations, submissions, approvals and pre-end (booking-ending-soon) mails. Add: pre-start booking reminders; check-in reminders before grace expiry (#1); auto-release notices (#1); threshold-based occupancy/utilization alerts for admins (rules + delivery). Optional SMS channel. | 2 wks (M) | None new for email (existing SMTP). Optional SMS = paid gateway (Twilio/MSG91). | Phase 1 / ongoing
Assessment grounded in the current codebase (desk bookings, occupancy_daily rollup, dashboards, cron + mailer, RBAC, floor-map picker + AI scan). %/effort are estimates for BRD planning.

## Gap Analysis
# | Requirement Area | Sub-Requirement | Status | % Built (est.) | What We Have (already built) | What It Requires (to build)
| 1. Auto-Release | Configurable check-in grace period | Not built | 0% | Per-facility pre_end_notify_minutes config pattern exists (reusable). | New grace-period setting (tenant/facility) + admin UI.
| 1. Auto-Release | Auto-release on no check-in | Not built | 10% | checkout_status enum placeholder; desk-hold + overlap model; CRON_SECRET job pattern. | Check-in action + checked_in_at; scheduled release job; 'released' status; free the desk.
| 1. Auto-Release | Pre/post-release notifications | Partial | 30% | Mailer + cron pre-end 'booking ending soon' mail already live. | New pre-release + post-release templates and triggers wired to the release job.
| 1. Auto-Release | Audit log of released bookings | Not built | 5% | updated_at timestamps on bookings; legacy_desk_id audit pattern. | Dedicated release audit table (who/when/why=system) + admin view.
| 2. Biometric | Integrate biometric/attendance system | Not built | 5% | HReVO data + integration contract docs drafted. | Vendor connector (API/webhook/file), attendance_events store, auth/mapping.
| 2. Biometric | Validate attendance vs reservation | Not built | 5% | bookings carry user_id + department_id; check-in model planned (#1). | Reconciliation engine matching attendance ↔ booking ↔ check-in.
| 2. Biometric | Report booked&used / no-show / walk-in | Not built | 0% | occupancy_daily fact table can host the measures. | Classification logic + report views (depends on check-in #1 + attendance feed).
| 2. Biometric | Compliance & utilization reports | Partial | 20% | Utilization rollup (occupancy_daily) + dashboards exist. | Compliance reports keyed on attendance reconciliation + BU dimension (HReVO).
| 3. Analytics | Real-time occupancy/utilization dashboard | Built | 85% | /api/dashboards/tenant-admin (occupied_now/free_now, per-facility open/booked minutes); Live Overview, Dashboard, Gantt timeline. | Minor polish; wire released/no-show once #1 lands.
| 3. Analytics | Analytics by location/building/floor/dept/BU | Partial | 55% | occupancy_daily carries site/building/floor/department dims; nightly aggregator. | Dept/floor/building slice UIs; BU dimension (needs HReVO, #2).
| 3. Analytics | Reports: occupancy trends / peak periods | Partial | 40% | Daily rollup + timeline give the raw data. | Dedicated trend & peak-period report views + date-range controls.
| 3. Analytics | Reports: no-show & released bookings | Not built | 5% | Reporting scaffolding (occupancy_daily). | Depends on check-in/release data from #1; new report views.
| 3. Analytics | Export Excel / PDF | Partial | 30% | Facilities list has a 'Download Excel' export. | Excel export for reports/occupancy (exceljs) + PDF renderer (pdfmake/puppeteer).
| 3. Analytics | Scheduled report email distribution | Not built | 10% | Cron + mailer infrastructure exist. | Report scheduler + recipient config + rendered-attachment emails.
| 4. UX | Interactive floor map w/ real-time availability | Built | 85% | DeskPicker SVG map, occupied/selected status, S/M/L dots, real-time occupied_desks via /bookings/check, VIP hiding. | Mobile polish; optional density/zoom controls.
| 4. UX | Search / filter by location, floor, etc. | Built | 80% | Facilities/bookings filters (site/building/floor/type) + text search; cascade filter. | Minor filter additions on the booker-facing views.
| 4. UX | Mobile-responsive booking | Partial | 60% | Responsive app shell (mobile slide-over), MUI responsive, scrollable picker. | Verify/tune floor-map picker + booking flow on small screens.
| 4. UX | QR check-in / check-out | Not built | 0% | Booking + (planned) check-in model. | QR generation per desk/booking + scan page driving check-in/out (#1).
| 4. UX | Team members' seating visibility (perm-based) | Not built | 10% | Desk_id per booking + RBAC permission matrix. | Seating overlay (who sits where) gated by a new permission + privacy controls.
| 5. Admin | Configurable booking rules | Built | 80% | Advance rules (min/max), approval chains, slot-capacity overrides, shared/exclusive, facility rules. | Expose grace period alongside existing rules.
| 5. Admin | Reservation limits & policy controls | Built | 90% | max_per_user_per_day/week/month, min_advance, max_advance enforced server-side + admin UI. | Minor: org-level policy presets if desired.
| 5. Admin | Desk blocking & maintenance | Partial | 25% | Facility-level status + offline_capacity; VIP chairs. | Per-desk block/maintenance windows (desk status + maintenance schedule).
| 5. Admin | Centralized admin dashboard | Built | 70% | Admin overview + masters + dashboards; RBAC incl. org_admin. | Add monitoring widgets + the new alerts (#6).
| 6. Notifications | Booking confirmations & reminders | Partial | 60% | Confirmation, submitted, approval, confirmed emails all live. | Pre-start booking reminders (scheduled).
| 6. Notifications | Check-in reminders before expiry | Not built | 15% | pre-end 'ending soon' cron + mailer pattern (reusable). | Check-in reminder tied to grace window (#1).
| 6. Notifications | Auto-release notifications | Not built | 10% | Mailer + cron infrastructure. | Release-event notifications (#1).
| 6. Notifications | Occupancy/utilization alerts for admins | Not built | 5% | occupancy_daily measures available. | Threshold rules + admin alert delivery (email/in-app).
| Legend: | Built | Partial | Not built | % Built = rough estimate of completeness vs the requirement.

## Roadmap & Effort
Phase | Focus (Requirement areas) | Scope highlights | Est. Duration | Key dependencies
Phase 1 | Auto-release (1) + related Notifications (6) | Check-in action, grace-period config, scheduled auto-release, release audit log, check-in reminders + release notices. Unblocks no-show/released reporting. | 3–4 wks | External scheduler, SMTP (both already in place).
Phase 2 | Analytics & Reporting (3) + Admin controls (5) | Reports module (trends, peak, released), Excel + PDF export, scheduled email distribution, per-desk blocking/maintenance, admin alerts. | 3–4 wks | exceljs/pdf libs (OSS); no-show/released data from Phase 1.
Phase 3 | Enhanced UX (4) | QR check-in/out flow, team-members seating visibility (permissioned), mobile-responsive polish of the floor-map picker. | 3–4 wks | QR libs (OSS); check-in model from Phase 1.
Phase 4 | Biometric Attendance Integration (2) | Biometric connector + attendance ingestion, reconciliation (booked&used / no-show / walk-in), compliance & utilization reports, BU dimension. | 4–6 wks+ | Biometric vendor API/SDK (licensed); HReVO employee-key mapping; BU source.
Indicative total | All 6 areas | Sequential (Phase 4 vendor-dependent). Phases 1–3 can partly overlap with parallel resources. | ~13–18 wks | Biometric vendor availability is the main schedule risk.
Area | Requirement | Est. % already built
1 | Automatic Release of Unutilized Desk Bookings | ~15%
2 | Biometric Attendance Integration | ~5%
3 | Advanced Analytics & Reporting Dashboard | ~45%
4 | Enhanced User Experience | ~55%
5 | Administrative Controls | ~65%
6 | Notifications and Alerts | ~45%

## Dev-Test-Deploy Timeline
Delivery Timeline — 3 Phases
Phase 1 Core enhancements (≤4 wks) → Phase 2 Integrations: WhatsApp + Teams calendar + Visitor Management (2–3 wks) → Phase 3 AI integration (5–6 wks).
Sequential; within each phase, development runs in parallel then Testing (2–3 d) + Deployment (1–2 d). Relative weeks — anchor Week 1 to your start date.
Track | Duration | Weeks
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
PHASE 1 — Core desk-booking enhancements (≤ 4 weeks)
Req 1 — Auto-release + check-in | ~2.5 wks
Req 2 — Biometric integration | ~3 wks
Req 3 — Analytics & reporting | ~3 wks
Req 4 — Enhanced UX (QR, team seating) | ~2.5 wks
Req 5 — Admin controls | ~2 wks
Req 6 — Notifications & alerts | ~1.5 wks
Testing (integration + UAT) | 2–3 d
Deployment (prod release) | 1–2 d
PHASE 2 — Integrations: WhatsApp · Teams calendar · Visitor Mgmt (2–3 weeks)
WhatsApp integration (book + notify via WhatsApp) | ~2 wks
Microsoft Teams calendar integration (2-way sync) | ~2 wks
Visitor Management System (invite, pass, check-in) | ~2 wks
Testing (integration + UAT) | 2–3 d
Deployment (prod release) | 1–2 d
PHASE 3 — AI integration (5–6 weeks)
Conversational booking assistant (NL via WhatsApp/Teams/web) | ~5 wks
Smart desk recommendations (team proximity, prefs, amenities) | ~4 wks
Calendar-aware auto-booking (reads Teams/Outlook) | ~4 wks
Predictive occupancy + no-show prediction | ~4 wks
NL desk search + NL analytics for admins | ~4 wks
Testing (integration + UAT) | 3–5 d
Deployment (prod release) | 1–2 d
Legend |  | Weeks W1: Development; Weeks W4: Testing; Weeks W7: Deployment
Total (sequential): | ~11–13 weeks | Weeks W2: P1 ~4 wks + P2 ~2–3 wks + P3 ~5–6 wks
Phase 3 — where AI eases desk-booking interaction
1. Conversational booking assistant | Book in plain language across WhatsApp / Teams / web — e.g. "book a desk near my team Tue–Thu, 10–4".
2. Smart desk recommendations | Best-fit desk from team proximity, past choices, required amenities (monitor/standing) and accessibility.
3. Calendar-aware auto-booking | Reads Teams/Outlook; auto-proposes or books desks only on your in-office days, cancels on WFH days.
4. Predictive occupancy & peak forecasting | Forecasts busy days/floors and nudges users to quieter alternatives; helps facilities plan capacity.
5. No-show prediction + proactive release | Flags bookings likely to go unused, prompts check-in, and frees desks early to raise utilization.
6. Natural-language desk search | "Quiet desk, dual monitor, 3rd floor, near a window" — AI filters the floor map instantly.
7. NL analytics for admins | Ask "which floor was least used last month?" and get an instant answer + chart (no report-building).
8. Team coordination | AI suggests a common in-office day for a team and books adjacent desks together.
9. Smart, personalized nudges | AI-timed reminders, check-in prompts and release warnings tuned to each user's pattern.